## Sprint 1 Plan
Issue # | Type | Title | Story Points | Due Date | Description / Associated Work | Priority | Risk (Why) | Responsible
#12 | US | User Registration | 3 | 2026-02-05 | Allow users to create an account with validation and secure storage | High | Medium – validation & DB integration | Backend
#4 | US | Login / Logout | 3 | 2026-02-05 | Enable user authentication sessions and logout functionality | High | Medium – session handling | Backend
#6 | US | Profile Management | 2 | 2026-02-05 | Allow users to edit profile, dietary preferences and allergies | Medium | Low – form handling | Frontend
#7 | Task | User Interface | 2 | 2026-02-05 | Create registration, login and profile pages (HTML/CSS) | High | Low – UI implementation | Frontend
#5 | Task | Password & Authentication | 3 | 2026-02-05 | Configure Django authentication and password hashing | High | Medium – security configuration | Backend
#11 | Task | Unit Test for Auth | 2 | 2026-02-05 | Write unit tests for authentication flows | Medium | Medium – testing setup | Backend
#10 | Task | Sprint 1 Demo | 2 | 2026-02-05 | Prepare working demo of at least one user account feature | High | Medium – demo stability | Team
#9 | Task | Sprint 1 Artifacts | 2 | 2026-02-05 | README, sprint plan, meeting minutes, contribution logs | High | Low – documentation | Kareem
#8 | Task | Database | 3 | 2026-02-05 | Configure user model and database schema | High | Medium – DB integration | Backend
#2 | Task | GitHub Setup | 1 | 2026-02-05 | Create repository structure and branching strategy | High | Low – setup task | Kareem
#1 | Task | Project Skeleton | 2 | 2026-02-05 | Initialize Django project and folder structure | High | Low – initial configuration | Backend