## Sprint Data Table Conversion
Issue # | User Story / Task Title | Points | Due Date | Description / Associated Tasks | Priority | Risk | Responsible
#56 | US08 - Weekly Calorie & Macro Breakdown | 5 | 2026-03-21 | Display total calories and macros for weekly meal plan with visual charts | High | Low | Mcwill Buikpor
#57 | Task08_01 - Calculate weekly nutrition totals | 2 | 2026-03-19 | Create utility functions to sum calories and macros, calculate percentages | High | Low | Mcwill Buikpor
#58 | Task08_02 - Create Macro Summary Card | 1 | 2026-03-20 | Build summary card displaying total calories, protein, carbs, fat (avg per day) | High | Low | Mcwill Buikpor
#59 | Task08_03 - Implement Macro Pie Chart | 2 | 2026-03-20 | Create interactive donut chart showing protein/carbs/fat using Recharts | High | Low | Mcwill Buikpor
#60 | Task08_04 - Implement Daily Calories Bar Chart | 2 | 2026-03-21 | Create bar chart showing calories per day across the week using Recharts | High | Low | Mcwill Buikpor
#61 | Task08_05 - Integrate into Meal Planner page | 1 | 2026-03-21 | Add macro section below meal grid; handle live data updates | High | Low | Mcwill Buikpor
#62 | AT08 - Weekly Macro Breakdown Display | - | 2026-03-22 | Verify breakdown displays correct totals and charts with sample data | High | Low | Mcwill Buikpor
#63 | AT09 - Macro Breakdown Live Updates | - | 2026-03-22 | Test that breakdown updates immediately when meals are added/removed | High | Low | Mcwill Buikpor